EE6008 COLLABORATIVE RESEARCH AND DEVELOPMENT PROJECT

Design and Implementation of UAV Motion State Based Covert Communications

Literature Guide and Project Charter

| Supervisor | Dr Shuping Dang |
| --- | --- |
| Team | [TO COMPLETE: names and matriculation numbers] |
| Team leader | [TO COMPLETE] |
| Project period | 13-week teaching term [dates to be confirmed] |
| Version | Draft v0.1 ¦ 17 August 2026 ¦ Supervisor review |

Project proposition. Build an end-to-end payload-to-motion-to-payload demonstrator in which an authorised visual receiver decodes keyed UAV micro-motions while an unauthorised observer has difficulty distinguishing encoded flight from nominal flight.

# Part I. Guided Reading of the Three Core References

The three references are complementary rather than interchangeable. Ref A is the strongest end-to-end implementation baseline; Ref B supplies the state quantiser and cascaded flight-control baseline; Ref C supplies a motion-shape library and a rigorous way to measure how visible flight gestures are to untrained observers. Their combination creates a credible project, but only if conspicuous communication gestures are separated from genuinely low-detectability micro-motions.

| Reference | Primary contribution | What it proves | Role in this project |
| --- | --- | --- | --- |
| A — MoCom | Motion alphabet, event-stream segmentation, SNN recognition, online decoder | A receiver can decode deliberately visible MAV actions | Reliable communication baseline and strong Bob/Willie |
| B — Motion-state covert | 16-bit state quantiser, 6DoF model, outer PID / inner PD | Observed flight states can be labelled as digital words | Simulation/control baseline; must add inverse encoder and LPD evaluation |
| C — Flight paths | Eight parametric gestures and human forced-choice study | Some large gestures convey intuitive public meanings | Conspicuous positive control and shape library; not a covert codebook |

## Recommended reading order

- Read Ref B first to understand the project title, 16-bit state representation and control architecture.

- Read Ref A second to see what a complete transmitter–observer–decoder loop requires in practice.

- Read Ref C third as a warning and a benchmark: motions that humans easily interpret are useful controls but are poor covert symbols.

## Ref A — MoCom: motion-based inter-MAV visual communication

MoCom encodes a navigation command as an eight-symbol visual frame: start, one direction bit, three heading bits, two distance bits and end. The actual information payload is therefore six bits; start and end are control symbols. Four visible motion primitives represent start, end, 1 and 0. A fixed event camera observes a Performer Crazyflie, segments a continuous event stream, classifies each action with EventMAVNet, and reconstructs the command with an online Integrated MAV Segmentation and Recognition (IMSR) state machine. The command is then sent through a conventional control link to an Executor Crazyflie.

Important interpretation. MoCom demonstrates reliable visual motion communication, not covertness. Its explicit start/end gestures, V-shaped symbols and long idle intervals are designed to be easy to recognise.

### Technical elements worth retaining

A framed protocol with start/data/end states, upgraded in this project with sequence number, CRC-8, timeout and optional Hamming coding.

A separate background/no-signal class, so the receiver must first decide whether a valid action exists.

Motion segmentation before classification. MoCom uses 33 ms event frames, positive-event ratio and local event-count variance, followed by temporal filtering.

Session-level tests at 0.9 m, 1.2 m and 1.5 m, plus symbol confusion matrices and temporal segmentation IoU.

EventMAVNet only as a stretch implementation. An RGB camera, ArUco tracking and trajectory features are the lower-risk MVP.

| Condition | Reported accuracy | Reported model energy | Interpretation |
| --- | --- | --- | --- |
| 0.9 / 1.2 / 1.5 m | 96.51 / 95.37 / 94.98% | Not reported end-to-end | High action-classification accuracy |
| 128×128, F=16 | 95.37% | 2.567 mJ | Highest-accuracy ablation point |
| 64×64 | 92.28% | 0.432 mJ | Practical course-project starting point |
| F=8 | 91.98% | 0.875 mJ | Lower temporal cost |

MoCom reports 1.26 ms per batch of ten samples on an RTX 4090; this is not an onboard Raspberry Pi latency. Its approximately three-second actions and three-second guard intervals imply roughly 45 seconds for a six-bit frame, or about 0.13 bit/s by engineering inference. The paper does not report BER, PER, repeated-trial confidence intervals or complete platform energy.

## Ref B — encoding UAV motion states

Ref B uses a six-degree-of-freedom quadrotor model, an outer position PID loop and an inner attitude PD loop. During a 15-second point-to-point flight, the simulated state is sampled every 20 ms and mapped into a 16-bit label. The fields cover distance from origin, position class, total and per-axis velocity conditions, and the signs of roll, pitch and yaw.

| Bits | Meaning | Replication note |
| --- | --- | --- |
| b1–b2 | Four distance bands | T1, T2 and T3 are not published |
| b3–b6 | 15 position classes: octants, planes, axes and origin | Equality-to-zero rules need tolerance and hysteresis |
| b7–b13 | Total speed plus per-axis sign and magnitude | Velocity thresholds are not published |
| b14–b16 | Signs of roll, pitch and yaw | Paper says rotation direction but tests angle sign |

Critical gap. The implemented direction is flight state → 16-bit state label. It does not yet provide arbitrary payload → feasible motion → independent observation → recovered payload. Nor does it define a Willie, H0/H1 test, false alarm, missed detection, ROC-AUC or detection-error probability.

### Elements to reproduce and extend

Reproduce the standard 6DoF plant and cascaded position-PID / attitude-PD architecture, validating any equation-level discrepancies against a trusted quadrotor model.

Retain the published 16-bit state label as a simulation baseline, not as an asserted 800 bit/s channel.

Add an inverse encoder that converts payload symbols into dynamically reachable state targets and smooth, bounded trajectories.

Add tolerance bands, hysteresis, timing recovery, CRC/FEC and an independent visual receiver.

Define normal flight H0 and encoded flight H1, then test covertness against a trained observer rather than relying on a secret fixed table.

## Ref C — communicative flight paths for sUAS

Ref C studies whether untrained people attach common meanings to eight biologically inspired, periodic flight paths: Circle, Figure-8, Left-Right, Loop, Spiral, Swoop, Undulate and Up-Down. A Firefly hexacopter followed large parametric trajectories under Vicon feedback and PID pose control; each gesture lasted about 30 seconds and occupied roughly 0.5–4 m. Sixty-four mTurk participants completed either a two-alternative or seven-alternative forced-choice video study.

| Gesture | Significant interpretation | Agreement |
| --- | --- | --- |
| Figure-8 | Lost sensor (2AFC) | 84.38% |
| Spiral | Landing (2AFC / 7AFC) | 87.5% / 59.4% |
| Swoop | Draw attention (2AFC) | 75% |
| Circle | Draw attention (7AFC) | 40.6% |
| Undulate | Draw attention (7AFC) | 34.4% |

Only Spiral → Landing remained stable across both choice conditions. Ref C is therefore not a digital code design: the mapping is many-to-one, prompted meanings can change, and no framing, synchronisation, BER or receiver is defined. Its high-salience trajectories are valuable as a non-covert positive control and as a public safety signalling layer.

## Cross-paper migration decision

Recommended synthesis. Use Ref B for modelling and control; Ref A for framing, segmentation and machine decoding; and Ref C for conspicuous baselines and optional public-safety gestures. The covert payload itself should use keyed, low-amplitude variations embedded in a nominal mission trajectory.

### Migration priorities

Transfer immediately: Ref B's cascaded controller and state logging; Ref A's framed protocol, background class and receiver state machine; Ref C's conspicuous shapes as positive controls.

Adapt before use: replace MoCom's long visible actions with bounded relative deviations; convert Ref B's state-to-word mapping into a feasible inverse planner; scale Ref C paths from metre-level gestures to centimetre-level templates.

Use two codebooks: an overt safety layer for public states such as landing/attention, and a separate keyed micro-motion layer for digital payload.

Use the same strong observer twice: as Bob when it knows timing/key, and as Willie when it does not. This exposes whether the gain comes from the key or simply from obvious flight anomalies.

Defer until the MVP works: event camera, SNN, dual-UAV relay, human-subject study and adversarial codebook optimisation.

The practical first experiment is therefore a fixed-height Crazyflie flight observed by an RGB camera: nominal waypoint paths define H0; Ref A/C-inspired large symbols validate the receiver and Willie; a keyed four-symbol micro-motion codebook defines H1. The experiment sweeps amplitude and duration to produce a BER–AUC–mission-overhead Pareto curve.

# Part II. EE6008 Project Charter

## 1. Charter metadata

| Project title | Design and Implementation of UAV Motion State Based Covert Communications |
| --- | --- |
| Course | EE6008 Collaborative Research and Development Project |
| Supervisor | Dr Shuping Dang |
| Team / leader | [TO COMPLETE] |
| Duration | 13 teaching weeks; approximately 6 hours per student per week |
| Budget ceiling | S$1,000 |
| Primary platform | Crazyflie-class indoor micro-UAV; simulation first |
| Submission milestones | Project Charter in Week 3; report and presentation videos in Week 13 |

## 2. Problem statement and opportunity

Conventional UAV communication relies on RF links that may be congested, jammed or undesirable in electromagnetically constrained environments. Existing motion-based approaches show that flight state can carry information, but leave a gap between state labelling and a complete, measurable communication system. The project will close that gap by implementing an independent visual receiver and by distinguishing content secrecy from low probability of detection.

## 3. Aim and research question

Aim. Design, implement and evaluate a safe indoor UAV demonstrator that transmits a short digital payload through controlled motion variations, while preserving nominal mission behaviour and measuring both authorised decoding reliability and unauthorised detectability.

Primary research question. Under flight-stability, task-path and energy constraints, can a keyed micro-motion codebook remain reliably decodable by an authorised visual receiver while being difficult for a no-key observer to distinguish from normal flight?

## 4. Objectives

- Reproduce a validated 6DoF quadrotor and cascaded position-PID / attitude-PD simulation based on Ref B.

- Implement a complete payload-to-motion-to-payload chain with framing, synchronisation, CRC and a safe four-symbol motion alphabet.

- Build an independent RGB visual receiver using marker tracking, filtering, action segmentation and symbol classification; use onboard telemetry only as ground truth.

- Establish a conspicuous motion baseline derived from Refs A/C and a keyed micro-motion scheme embedded in nominal waypoint flight.

- Evaluate reliability, control quality, mission overhead and statistical covertness on held-out flight sessions.

- Deliver reproducible code, logged data, a hardware demonstration, a technical report and the required presentation videos.

## 5. Scope

### In scope

Single transmitting UAV, fixed external Bob camera and software Willie; indoor, fixed-height hardware trials.

Full 3D state quantisation and cascaded controller in simulation; local x/y/yaw micro-motion subset on hardware.

Four motion primitives (2 bits/symbol) for the MVP, with keyed permutation and multiple near-equivalent variants where time permits.

Comparison of nominal flight, conspicuous Ref A/C-style communication and proposed micro-motion communication.

RGB receiver as MVP; event camera and SNN only if suitable hardware, data and time are available.

### Out of scope

Outdoor or beyond-visual-line-of-sight operation, payload delivery, autonomous swarms or adversarial manoeuvres.

A custom low-level flight-controller firmware, RF covert waveform design or cryptographic security proof.

Human-subject experiments unless separate ethics approval and supervisor direction are obtained.

Claims of formal LPD capacity or the square-root law; the project provides empirical detectability evidence for a defined observer.

## 6. System concept and threat model

Payload → keyed frame → motion-symbol planner → bounded trajectory smoother → cascaded controller → UAV → external visual state estimator → action segmentation → symbol decision → CRC → recovered payload

### Actors and hypotheses

Alice is the transmitting UAV. Its safety/control RF link carries no communication payload.

Bob is an authorised external visual receiver that knows symbol timing and the keyed codebook. Bob must decode without reading UAV telemetry.

Willie has a comparable line of sight and may train on example flights, but does not possess the session key. Willie decides between H0 (nominal mission) and H1 (same mission with embedded payload).

The public algorithm may be known. Covertness must therefore be measured by detectability of H1, not by assuming the codebook remains permanently secret.

## 7. Proposed technical design

### MVP protocol

Keyed preamble | sequence number | payload | CRC-8 | optional Hamming(7,4)

Four fixed-height relative primitives initially represent 00, 01, 10 and 11 through small left/right deviations and curvature/speed variants around the nominal path.

Begin with 10–20 cm deviation and 1.5–2.5 s symbols, then reduce amplitude and duration according to Bob BER and Willie AUC.

Apply jerk-limited or minimum-jerk smoothing and enforce velocity, acceleration, tilt, geofence and actuator limits.

Use telemetry and Lighthouse/Flow positioning only for control and ground truth; Bob receives pixels or extracted external-camera tracks.

### Software chain

MATLAB/Simulink or a verified Python 6DoF model for Ref B reproduction; Crazyflie cflib for safe high-level setpoints; Python, NumPy/SciPy and python-control for planning and analysis; OpenCV ArUco for pose tracking; Kalman/low-pass filtering for state estimation; scikit-learn or XGBoost for Willie; pandas/Parquet, YAML configuration, pytest and Git for reproducibility. PX4/ROS 2/Gazebo and SpikeJelly are stretch dependencies, not MVP requirements.

## 8. Success criteria and experimental design

| Dimension | Metric | Minimum evidence | Target / interpretation |
| --- | --- | --- | --- |
| Reliability | BER, PER, sync rate | ≥20 independent flights/condition where feasible | PER success ≥90%; BER ≤5% nominal |
| Control | RMSE, overshoot, settling, jerk | Telemetry ground truth and external track | Position RMSE ≤0.10 m nominal |
| Mission | Path/time/energy overhead | Matched H0/H1 waypoint missions | Time/energy overhead ≤15% |
| Covertness | ROC-AUC, PFA, PMD, ξ*=min(PFA+PMD) | Held-out flight sessions; 95% CI | Research target AUC ≤0.65 or ξ* ≥0.8 |
| Positive control | Willie AUC on conspicuous gestures | Ref A/C-style large-motion baseline | Clearly more detectable than micro-motion |
| Reproducibility | One-command analysis and configuration log | Fresh rerun before submission | All figures traceable to raw runs |

The AUC/DEP value is a research target, not a pass/fail promise. A well-controlled negative result showing that a proposed codebook is detectable remains valid if the reliability and evaluation pipeline are complete.

### Experiment matrix

Baseline B0: nominal waypoint flight with no payload (H0).

Baseline B1: conspicuous start/0/1/end or Ref C shape gestures; validates segmentation and Willie sensitivity.

Method M1: fixed low-amplitude motion codebook.

Method M2: keyed/randomised micro-motion codebook embedded in the same mission path.

Ablations: amplitude, symbol duration, camera distance/angle, light, fan disturbance, filtering, CRC/FEC and codebook key knowledge.

## 9. Work packages and deliverables

| WP | Work package | Owner role | Exit evidence |
| --- | --- | --- | --- |
| WP1 | Literature, threat model and protocol | Communications lead | Approved scope, codebook and metrics |
| WP2 | 6DoF model, controller and trajectory safety | Control lead | Validated tracking plots and tests |
| WP3 | Visual receiver and decoder | Perception lead | Offline and live symbol confusion matrix |
| WP4 | Willie detector and covertness analysis | Data lead | Held-out ROC/AUC/DEP pipeline |
| WP5 | Hardware integration and flight trials | Integration/safety lead | Repeatable demonstration and raw logs |
| WP6 | Report, videos and reproducibility | All; editor assigned | Final package and contribution log |

## 10. Milestones

| Week | Primary work | Gate / output |
| --- | --- | --- |
| 1 | Confirm interpretation, equipment, roles and safety | Supervisor decisions recorded |
| 2 | Threat model, literature matrix, MVP metrics; order hardware | Scope frozen for Charter |
| 3 | Submit Charter; repository and nominal simulator | Charter + baseline trajectory |
| 4 | Ref B 6DoF and cascaded controller reproduction | Tracking and equation checks |
| 5 | Frame, inverse encoder, planner and unit tests | Synthetic payload round trip |
| 6 | Receiver tracking, filtering and segmentation | Offline video decode |
| 7 | End-to-end simulation and conspicuous baseline | B1 confusion matrix |
| 8 | Willie H0/H1 pipeline and micro-motion search | First BER–AUC trade-off |
| 9 | Hardware commissioning; normal flight only | Failsafe and logging sign-off |
| 10 | Encoded hardware flights and matched H0/H1 data | Dataset complete |
| 11 | Statistical analysis, ablations and confidence intervals | Figures frozen |
| 12 | Report/video draft; only critical reruns | Internal review |
| 13 | Fresh reproducibility run and submission | Report + team/individual videos |

## 11. Resources and budget

| Item | Plan | Budget (S$) | Decision rule |
| --- | --- | --- | --- |
| Micro-UAV + radio + optical-flow deck | Crazyflie-class bundle | 550 | Use lab stock first |
| RGB camera and tripod | 60 fps preferred | 100 | Use existing camera if adequate |
| Batteries, charger, props/motor spares | Flight consumables | 90 | Purchase early |
| Safety net, prop guards, landing mat | Indoor safety | 80 | Mandatory before trials |
| Markers, printing, fan and fixtures | Experiment support | 40 | Low-cost/local fabrication |
| Freight/tax/contingency | Reserve | 140 | Do not buy event camera |

Total planned ceiling: S$1,000. An event camera and Lighthouse system are laboratory-loan/stretch resources only; purchasing them would displace core safety and flight hardware.

## 12. Risks, safety and ethics

| Risk | Likelihood / impact | Mitigation | Trigger / fallback |
| --- | --- | --- | --- |
| Hardware delay/failure | M / H | Order by Week 2; keep simulation-first path | Deliver SITL + recorded-video receiver |
| Visual tracking unreliable | M / H | Marker, calibration, good light, filtering | Increase symbol time/amplitude; offline decode |
| Codebook is detectable | H / M | Treat as research result; keyed variants and smoothing | Report Pareto boundary, not unsupported covert claim |
| Scope creep | H / H | MVP freeze in Week 3; event/SNN/dual-UAV are stretch | Drop stretch tasks after missed gate |
| Unsafe flight | L / H | Indoor cage, prop guards, ≤1 m, spotter, e-stop | Abort and revert to prop-off/SITL tests |
| Data leakage/overfit | M / H | Split by flight session; frozen test set | Repeat with new sessions |
| Human-subject approval | M / M | No participant study in MVP | Use ML Willie and archived/public stimuli |

## 13. Governance and change control

The team leader maintains the task board, weekly decisions, contribution log and experiment register.

A configuration file and immutable run identifier link every plot to code version, hardware condition and raw data.

Changes affecting scope, safety, budget or success metrics require supervisor approval and an updated Charter decision log.

A weekly 15-minute integration review checks the next gate, blockers, ownership and evidence, not only activity.

The report will distinguish measured covertness from message confidentiality and will document negative results and limitations.

## 14. Immediate supervisor decisions requested

- Can the original Ref B Simulink model, scripts, thresholds and controller settings be shared, and are the identified equation inconsistencies known errata?

- Is the intended payload arbitrary user data, or is the goal only to broadcast the UAV's observed state?

- Must the final receiver be an independent camera, or is telemetry-based decoding acceptable for any assessed component?

- Should formal H0/H1 low-probability-of-detection metrics be treated as a required outcome?

- Which UAV, positioning, camera, event-camera and safety facilities are available in the laboratory?

- Does the supervisor prefer exact Ref B reproduction before the micro-motion extension, or a reduced fixed-altitude implementation from the outset?

## 15. Approval

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Supervisor | Dr Shuping Dang |  |  |
| Team leader | [TO COMPLETE] |  |  |
| Team members | [TO COMPLETE] |  |  |

# References

[A] N. Zhang, H. W. Ho and Y. Zhou, “MoCom: Motion-Based Inter-MAV Visual Communication Using Event Vision and Spiking Neural Networks,” IEEE Transactions on Robotics, vol. 42, pp. 1680–1694, 2026. DOI: 10.1109/TRO.2026.3677077. Publisher link

[B] F. Yu, J. Ye, S. Dang, M. Kaneko, R. M. Shubair and M. Chafii, “Covert Communications by Encoding UAV Motion States: Joint Design of Codebook and Controller,” IEEE ICC, pp. 1808–1813, 2025. DOI: 10.1109/ICC52391.2025.11161329. Publisher link

[C] B. A. Duncan, E. Beachly, A. Bevins, S. G. Elbaum and C. Detweiler, “Investigation of Communicative Flight Paths for Small Unmanned Aerial Systems,” IEEE ICRA, pp. 602–609, 2018. DOI: 10.1109/ICRA.2018.8462871. Publisher link

[D] EE6008 Course Information and Schedule, Collaborative Research and Development Project, course document supplied to the team.